## Project Risk Rating
ASSIGNED CERTIFIER/(ARCHITECT) - INSPECTION NOTIFICATION FRAMEWORK FOR A SINGLE DWELLING - DRAFT
| X | X |  | X |  | X |  |  |  |  | X
ASSIGNED CERTIFIER/(ARCHITECT) - RISK ASSESSMENT FOR A SINGLE DWELLING - DRAFT
| X | X | X | X | X | X
ASSIGNED CERTIFIER/(ARCHITECT) - PRELIMINARY INSPECTION PLAN FOR A SINGLE DWELLING
| X | X | X | X | X | X | X | X | X | X | X | X | X
WORK STAGES |  |  | INSPECTION ASSESSMENT |  | INSPECTION SCHEDULE | [7 empty] | NOTES
Sample inspection Matrix Based on Code of Practice for Inspecting and Certifying Building works 2014 and Professional Judgement.
| Work stages (Note 4) | Elements to be inspected at each stage . | Item(s) to inspect. | Priority (H - Hold, W-Witness) | Contractor Notification Period | No of Inspectios by Assigned Certifier | Date | Follow up | Date | Sign off | 3rd Party Certification / Tests/ Samples | Inspections to be carried out by ancillary certifier (refer to attached anccillary certifier inspection plans) | Note/comment
1 | Commencement
Total no. of inspection Stage 1
2 | Excavations
Total no. of inspections Stage 2
3 | Covering foundations
Total no. of inspections Stage 3
4 | Rising walls to d.p.c.
Total no. of inspections Stage 4
5 | Underground services
Total no. of inspections Stage 5
6 | Radon barrier
Total no. of inspections Stage 6
7 | Floor insulation
Total no. of inspections Stage 7
8 | Timber frame
Total no. of inspections Stage 8
9 | Superstructure
Total no. of inspections Stage 9
10 | Superstructure completions
Total no. of inspections Stage 10
11 | First fix
Total no. of inspections Stage 11
12 | Plasterboarding
Total no. of inspections Stage 12
13 | Second fix
Total no. of inspection Stage 13
14 | Completions
Total no. of inspection Stage 14
GUIDANCE NOTES
Note 1 If an element is important because it is complex or will be repeated through a significant part of the building then that element must be inspectd during the early course of construction .
Note 2 Early assessment of the contractor's ability to carry out work is essential in estimating the number of sample inspections.
Note 3 This matrix should be expanded to reflect the scale and complexity of the project and the contractor's programme.
Note 4 In order to facilitate co-ordination of work stages between disciplines the main work stages should be identified and agreed by all those carrying out inspections.
Note 5 The inspection regime must be appropriate and must be kept under review at all times.
Note 6. The timing of inspections must correspond with the work being undertaken on site.
Note 7. The Assigned Certifier/Architect should normally expect to carry out some unanounced inspections.
Note 8 Follow up procedures are essential to ensure that non-compliance issues identified during inspections are resolved.
Note 9 The Assigned Certifier/Architect should indicate in the inspectin plan the tests they wish to have carried out.
Note 10 Records of inspections must be maintained, sufficient the work inspected and any non-compliance issues notd.
Note 11 Additional inspections are likely to be required for quality control purposes.